## Sheet1
Feature | Estimate | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Owner | Status | Remarks
Requirement Analysis | 16 hrs | 2014-12-23 | 2014-12-24 | 2014-12-23 | 2014-12-24 | Vignesh | Complete
Design – HLD & Planning | 24 hrs | 2014-12-26 | 2014-12-30 | 2014-12-26 | 2014-12-30 | Vignesh | Complete
Database Design | 40 hrs | [6 empty] | DB Design has to be done simultaneously during development of modules. One developer will be involved in DB design during initlal phase
Core Customization | 40 hrs |  |  | 2014-12-31 | 2015-01-07 | Vignesh | Complete | 1. Customizing the API Authorization and Include Custom Modules for Gama in the backend application. 2. Setup base for the front application using angularjs.
Pick Up Point Selection | [6 empty] | Complete | 1. Modified default magento database for this module. Spent nearly additional 6hrs for this. Should be burnt in Database Design 2. Added a new module in frontend and backend.
Pick up point selection | 16 hrs | 2014-12-31 | 2015-01-05 | 2015-01-08 | 2015-01-09 | Vignesh | Complete | Added new API for listing Pickup Point Selection
Pick up point management | 16 hrs | 2015-01-06 | 2015-01-07 | 2015-01-12 | 2015-01-13 | Vignesh | Complete | Added a custom page in the backend for managing city and pickup points
Notify me for addition of pickup point | 16 hrs | 2015-01-08 | 2015-01-09 | 2015-01-13 | 2015-01-13 | Vignesh | Complete | 1. Added new API for the user to request new pickup point 2. Added a custom page in the backend for listing the requested
User Manipulation
Login | 16 hrs | 2015-01-12 | 2014-12-13 | 2015-01-13 | 2015-01-14 | Vignesh | Complete | 1. Added a new API for creating session 2. Added a authorization service in frontend which can act more generic. So, going forward adding new authorization will be easier
Register | 24 hrs | 14-01-2015 04-02-2015 | 19-01-2015 06-02-2015 13-02-2015 | 2015-02-04 | 2015-02-13 | Elangovan Marappan
Make your Order
Product / Inventory Management | 40 hrs | 2015-02-16 | 2015-02-20 | 2015-02-16 08:00 | 2015-02-20 17:00 | Elangovan Marappan | Complete
Day / Meal Selection-UI | 56 hrs | 19-02-2015 23-02-2015 | 10-03-2015 03-03-2015 | 2015-02-23 08:00 | 2015-03-03 17:00 | Elangovan Marappan | Complete
Day / Meal Selection-Backend | 24 hrs | 23-02-2015 04-03-2015 | 25-02-2015 06-03-2015 | 2015-03-04 08:00 | 2015-03-06 17:00 | Elangovan Marappan | Complete
Product Listing-UI | 40 hrs | 11-03-2015 09-03-2015 | 24-03-2015 13-03-2015 | 2015-03-09 08:00 | 2015-03-13 17:00 | Elangovan Marappan | Complete
Product Listing-Backend | 24 hrs | 26-02-2015 16-03-2015 | 02-03-2015 18-03-2015 | 2015-03-16 08:00 | 2015-03-18 17:00 | Elangovan Marappan | Complete
Make your combo--UI | 24 hrs | 25-03-2015 19-03-2015 | 01-04-2015 23-03-2015 | 2015-03-19 08:00 | 2015-03-23 17:00 | Elangovan Marappan | Complete
Make your combo-Backend | 40 hrs | 03-03-2015 24-03-2015 | 09-03-2015 30-03-2015 | 2015-03-24 08:00 | 2015-03-30 17:00 | Elangovan Marappan | Complete
Combo Product Altering--UI | 24 hrs | 02-04-2015 31-03-2015 | 09-04-2015 02-04-2015 | 2015-03-31 08:00 | 2015-04-06 17:00 | Elangovan Marappan | Complete
Combo Product Altering-Backend | 32 hrs | 10-03-2015 06-04-2015 | 13-03-2015 09-04-2015 | 2015-04-07 08:00 | 2015-04-10 17:00 | Elangovan Marappan | Complete
Addons – Single--UI | 08 hrs | 10-04-2015 10-04-2015 | 13-04-2015 10-04-2015 | 2015-04-14 08:00 | 2015-04-15 17:00 | Elangovan Marappan | Complete
Addons – Single-Backend | 32 hrs | 16-03-2015 14-04-2015 | 19-03-2015 17-04-2015 | 2015-04-16 08:00 | 2015-04-22 17:00 | Elangovan Marappan | Complete
Addons – Multiple-UI | 08 hrs | 14-04-2015 20-04-2015 | 15-04-2015 20-04-2015 | 2015-04-23 08:00 | 2015-04-24 17:00 | Elangovan Marappan | Complete
Addons – Multiple-Backend | 32 hrs | 20-03-2015 21-04-2015 | 25-03-2015 24-04-2015 | 2015-04-27 08:00 | 2015-05-04 17:00 | Elangovan Marappan | Complete
View My Cart
Cart Functionality | 24 hrs | 26-03-2015 27-04-2015 | 30-03-2015 29-04-2015 | 2015-05-11 | 2015-05-14 | Irudhayaraj | Complete
Order Summary | 40 hrs | 2015-04-30 | 2015-05-07 | 2015-05-15 |  | Irudhayaraj | In-progress
Alcarta Editing | 32 hrs | 31-03-2015 08-05-2015 | 03-04-2015 13-05-2015 | 2015-05-18 |  | Irudhayaraj | In-progress
Door Delivery | 16 hrs | 06-04-2015 14-05-2015 | 07-04-2015 15-05-2015 |  |  | Irudhayaraj
BYOV Discount | 12 hrs | 08-04-2015 18-05-2015 | 09-04-2015 19-05-2015 |  |  | Irudhayaraj
Invoicing | 24 hrs | 09-04-2015 19-05-2015 | 14-04-2015 22-05-2015 |  |  | Irudhayaraj
Payment
Payment Options Listing | 16 hrs | 14-04-2015 22-05-2015 | 16-04-2015 26-05-2015 |  |  | Irudhayaraj
Payment Gateway Integration (with one payment gateway) | 48 hrs | 16-04-2015 26-05-2015 | 24-04-2015 03-06-2015 |  |  | Irudhayaraj
Order Confirmation
Order Confirmation page | 16 hrs | 24-04-2015 03-06-2015 | 28-04-2015 05-06-2015 |  |  | Irudhayaraj
Order Management | 16 hrs | 28-04-2015 05-06-2015 | 30-04-2015 09-06-2015 |  |  | Irudhayaraj
Order Listing for Kiosk / Delivery Person | 16 hrs | 30-04-2015 09-06-2015 | 04-05-2015 11-06-2015 |  |  | Irudhayaraj
Delivery and Pick Up Time | 8 hrs | 04-05-2015 11-06-2015 | 05-05-2015 12-06-2015 |  |  | Irudhayaraj
Note on I5: atin.kumar: This was not a planned activity.

## Sheet2
2015-02-16 08:00 | 2015-02-20 17:00
2015-02-23 08:00 | 2015-03-03 17:00
2015-03-04 08:00 | 2015-03-06 17:00
2015-03-09 08:00 | 2015-03-13 17:00
2015-03-16 08:00 | 2015-03-18 17:00
2015-03-19 08:00 | 2015-03-23 17:00
2015-03-24 08:00 | 2015-03-30 17:00
2015-03-31 08:00 | 2015-04-06 17:00
2015-04-07 08:00 | 2015-04-10 17:00
2015-04-14 08:00 | 2015-04-15 17:00
2015-04-16 08:00 | 2015-04-22 17:00
2015-04-23 08:00 | 2015-04-24 17:00
2015-04-27 08:00 | 2015-05-04 17:00
2015-05-05 08:00 | 2015-05-07 17:00
2015-05-08 08:00 | 2015-05-14 17:00
2015-05-15 08:00 | 2015-05-18 17:00
2015-05-19 08:00 | 2015-05-20 12:00
2015-05-20 13:00 | 2015-05-25 12:00